## Sheet1
Characteristics: | Software Development Lifecycles
| Waterfall Model | V Model | Iterative Model | Spiral Model | Agile approach
1. Category | The Waterfall Model is “Plan-Driven” meaning it is done in quential/incremental phases. It is done in a step-like fashion, on each step there is a new phase with the team being unable to progress through the model without completing the previous step. | V- model is plan driven as opposed to agile approach the coding and testing phase have more focus than the design phase. In comparison in the V-model the design phase gains more focus than the implementation phase. | The Iterative Model is Plan Driven and was designed as an improvement to the existing waterfall model. The waterfall model is a linear SDLC model whereas the iterative model is cyclical in nature | Spiral Model is plan driven and prototyping based as it is done in 4 phases. It is done in an incremental pattern and it spirals out developing a project as it continues outwards.
2. Planning | In the planning phase the aim is to leave this phase with a clear goal in mind in the up-and-coming steps. At this point the requirements must be given clearly and accurately with each member being assigned a specific task at hand. | Testing activities like planning happen well before coding. This saves a of time. Requirements should be clearly defined at this point. | The Planning stage is used to map out the requirements. Be it either hardware or software. In the planning stage you also prepare for the other stages to follow. | The difference between this approach and others is that spiral model focuses on risk and prototyping. This model begins with risk analysis and planning and then progresses through to requirements.
3. Requirements | Requirements are the goals of the project. The aim of the Waterfall Model is to budget and channel funding into the best performing channels within development. They are supposed to be given clear and concisely. The requirements come from the customer to the team and they are the aims of the project. The requirements should be designed with the customers interest at hand. They are “Customer Focused”. | The first phase of development is business requirements where the product requirements are outlined and communication with the customer is required to gain understanding of the requirements. The goals are mainly Validation and verification of requirements are a critical part. | development begins by specifying and implementing just part of the software, which can then be reviewed in order to identify further requirements. This process is then repeated, producing a new version of the software for each cycle of the model. | The first phase of this project is to prototype a function program so that the client can input ino it production.Goals of the project are to maintin a strict budget in both high risk applications and also high budget projects. Requirements are changing constantly through the client. Client is hands on with project.
4. Design | The design phase specifies the hardware as well as system requirements that are required to further the project. This includes the programming language in question as well as the system architecture. The design phase can be further split into a “high” and “low” phase. In the high level phase data such as diagrams based on the overall architecture are included. But in the lower phase it is more code focused. This includes pseudo-code and also error fixing. | Plan programming languages like java or databases like MySQL for example. Which would be suitable for the project? Under the V-Model, the corresponding testing phase of the development phase is planned in parallel. So, there are Verification phases on one side of the ‘V’ and Validation phases on the other side. The Coding Phase joins the two sides of the V-Model. | The Design stage is where many potential solutions for the project are analyzed. The solutions are narrowed down. After that, the most effective and efficient way to construct the system is decided. The team on the project should have a complete set of requirements to work from along with the direction which is to be taken for the project and Conceptual Systems Design. | The spiral model has four phases: Planning, Design, Construct and Evaluation. Designed to slowly release a final product and to refine it as we go along.The hardware and software are predefined at the beginning of the project. Designed to manage and overcome unknown risks that may develop In the different phases as the project progresses. Prototyping at the beginning of each planning phase is very important. Designed to include client in the whole process.
5. Build | Requirements such as how many users will use the applications are all key aspects to consider during the build phase of the application. The requirements do not adapt or change from the outset. | After the Design stage you go ahead to the build stage, this is where the actual coding takes place following the guidelines we have previously set.This model is used for simple low risk / low budget projects. Requirements are clear from outset | In this stage feature code is designed, developed and tested in repeated cycles. | Not advised for low risk / small products as cost is higher than other models due to excess planning and prototyping. Building occurs slowly as requiremnts change and adopt due to customer input.
6. Testing | Testing allows for the standard of the application to maintain at a high level. Testing is allowed and needed to ensure that the requirements stay true to the original requirements of the customer.(Good contrast to spiral) | Main principle in V-Model is to start testing early. Reviews, walkthroughs and inspections of documents during the definition stages are examples of early tests. Prepare test cases early. Unit Testing: designed in the module design phase are executed on the code during this phase. Integration Testing: is associated with the architectural design phase. System Testing: is directly associated with the system design phase. System tests check the entire system functionality and the communication of the system under development with external systems. Acceptance Testing: is associated with the business requirement analysis phase and involves testing the product in user environment. Acceptance tests uncover the compatibility issues with the other systems.(Line 69 info expanded) | In the testing phase the current build iteration is tested against some standards and norms to check if they satisfy them. These testing procedures are set in place to find out any bugs or errors in our system. | Testing happens after the risk analysis phase and is very important in the spiral model This is done through a use of prototyping and iterative sprints through all four processes of the model. Work closely to get customer feedback and help to change requirements.
7. Deployment | Deployment in the waterfall model occurs after the testing phase has been complete. This phase is when the project goes live and as such it is important to ensure that all the proper testing and error checking has been carried out. | In V-model deployment happens when all test have been passed in the verification and validation tests.At this stage all bugs from the unit testing and all other testing phases have been indentified and eliminated. | Iterative development contrasts with a traditional waterfall method in which each phase of the software development life cycle is “gated.” Coding doesn’t begin until design of the entire software application is complete and has gone through a phase gate review. Likewise, testing doesn’t begin until coding is complete and has passed necessary phase gate reviews. | Stepwise approach in 4 sectors. Uses prototyping approach before production. (Allows to find problems with main features before the project properly begins) Mainly used to approach high risk projects. Discussion at every interval to determine next feature to develop Can use it with scrum to adapt to changing requiremnts quickly.
8. Application*Line 71* | · Requirements are well defined, clearly documented and fixed. · Product definition is stable. · Technology is not dynamic and is well understood by the project team. · There are no ambiguous or undefined requirements. · The project is short. | · Requirements are well defined, clearly documented and fixed. · Product definition is stable. · Technology is not dynamic and is well understood by the project team. · There are no ambiguous or undefined requirements. · The project is short. |  | Used when projects are too ambitious and requirements may not be possible.
9. Maintenance | Software is constantly changing and improving and as so needs regular updates. Maintenance is carried out to allow for the product to remain functional and provide longevity to the project. | Once your system is ready to use, you may require to change the code later on as per customer request, But because requirements were well defined and tested pre deployment maintanance is minimal. | An iterative maintenance approach covers the common development steps of requirements, design, code, and test and verify results. This iterative flow is roughly the same as a complete software project and includes a benefits analysis. | Customer is very active in the build and testing of the spiral model and therefore the maintanance is higher than other projects, along wiht the fact it is high risk meaning revisiting is important.
10. Risk analysis | In the waterfall model the risk lies in the fact that once you move onto the next phase of the model you are unable to return to the previous stage of the model once they have been already complete. | In the V-model the risk lies in the fact that once you move onto the next phase of the model you are unable to return to the previous stage of the model once they have been already complete. This is made less risky then the waterfall model due to parrallel testing. | Iterative risk analysis is an established approach that uses a monitoring, research, evaluation and learning process (cycle) to improve future management strategies. The approach is very flexible, and can be applied to projects or sector analysis. | Risk analysis is very important in the model due to the nature of the projects taken on. The risk analysis is done in every phase of the project in order to eliminate breakdown or potential attacks on the deployed product. The risk is also offset at the beginning of ever project spiral as a prototype is made to find potential bugs and errors before the phases begin. The risk is furher brought down due to the customer being able to adapt their requirements before the phases begin because of the prototype.
11. Pros | Timescales are kept No financial surprises Testing is made easy The outcome is crystal clear Deal with issues in the design Potential development issues can be researched and tackled in the design stage - and alternative solutions planned - before any programming takes place What you plan is what you get | This is a highly-disciplined model and Phases are completed one at a time. Works well for smaller projects where requirements are very well understood. Simple and easy to understand and use. Easy to manage due to the rigidity of the model. Each phase has specific deliverables and a review process. | Generates working software quickly and early during the software life cycle. less costly to change scope and requirements. Easier to test and debug during a smaller iteration. Easier to manage risk because risky pieces are identified and handled during its iteration. | Software is produced early in the software life cycle. Risk handling Flexibility in requirements Good for large projects Good for customer satisfaction Suitable for expensive high risk projects
12. Cons | Needs can be difficult to define Clients may find it challenging to conceptualise their needs in terms of a functional specification during the requirements phase. This means that they may change their minds once they see the end product, which is difficult to address if the application needs to be re-engineered to any large extent. Projects may take longer to deliver, compared to using an iterative methodology such as Agile. | High risk and uncertainty. Not good for complex projects. Poor model for long projects. Not suitable for changing requirements. Cant go back when testing | More resources may be required. More management attention is required. It is not suitable for smaller projects. Highly skilled resources are required for skill analysis. | Not suitable for small projects due to cost. More complex than other sdlc’s. Too much dependence on risk analysis. Difficulty in time estimation due to unknown number of phases. Hard to define objective due to requirements.
Characteristics: | Software Development Lifecycles
| Waterfall Model | V Model | Iterative Model | Spiral Model
V-Model testing extra information. |  | These UTPs(Unit Test Plans) are executed to eliminate bugs at an early stage. This stage does not eliminate all the bugs. [10:59] Integration tests are performed to test the coexistence and communication of the internal modules within the system. [11:00] Most of the software and hardware compatibility issues can be uncovered during this system test execution. [11:00] available in the user environment. It also discovers the non-functional issues such as load and performance defects in the actual user environment.
Application extra information |  | V- Model application is almost the same as the waterfall model, as both the models are of sequential type. Requirements have to be very clear before the project starts, because it is usually expensive to go back and make changes. This model is used in the medical development field, as it is strictly a disciplined domain. The following pointers are some of the most suitable scenarios to use the V-Model application.
Extra Info Pros | Pros of Waterfall:
Since technical documentation is a necessary part of the initial requirements phase, this means that everyone understands the objectives. New developers can get up to speed quickly - even during the maintenance phase.
Pro: Timescales are kept
The phased development cycle enforces discipline. Each step has a clearly defined starting point and conclusion, which makes progress easy to monitor. This helps reduce any project "slippage" from agreed timescales.
Pro: No financial surprises
Costs can be estimated with a fairly high degree of accuracy once the requirements have been defined.
Pro: Testing is made easy
Test scenarios are already detailed in the functional specification of the requirements phase, which makes the testing process easier and more transparent.
Pro: The outcome is crystal clear
Even before the software development starts, the design is hammered out in detail which makes the needs and the outcome clear to everyone.
Pro: Deal with issues in the design Potential development issues can be researched and tackled in the design stage - and alternative solutions planned - before any programming takes place.
Pro: What you plan is what you get
Many organisations appreciate the attention to documentation right at the beginning, as it also means there should be no surprises with the end product.
Cons of Waterfall:
Con: Needs can be difficult to define
Clients may find it challenging to conceptualise their needs in terms of a functional specification during the requirements phase. This means that they may change their minds once they see the end product, which is difficult to address if the application needs to be re-engineered to any large extent.
Con: Potential lack of flexibility
There may be issues with the flexibility of the model to cater for new developments or changes of requirements which may occur after the initial consultation. Changes due to business plans or market influences may not have been taken into account when planning is all done up front.
Con: Longer delivery time
Projects may take longer to deliver, compared to using an iterative methodology such as Agile.